## Slide 1: GPI Integration GPF Project Charters
March 03, 2014

## Slide 2: Charter: Developer Productivity – Cycle time
Project Description Reduce Cycle Time for development and drive efficiency by providing environments to developers faster Cycle Time also leverages the operational enhancements provided by GPF’s GPaaS offering. New and improved platforms will be introduced in the GPaaS environment.
Goal Improve developer productivity by reducing the Cycle Time from development to deployment.
Deliverables Provide an interface to all aspects of PaaS including provisioning, deployment and monitoring Implement Unified Deployment System for GPaaS to support all eBay Inc. stacks Enhance provisioning to be more robust and run on OpenStratus Introduction of Kraken (Node.js) and Java development on GPaaS Optimization of C++ on GPaaS
Dependencies GCS - One cloud for MP and PP GDI - Implement Next Gen DALL for a persistence layer with eBay scalability, availability and manageability Enable CaaS on Couchbase and operationalize throughout eBay Inc. GESE - Tools strategy for supporting virtualized environment GTO - Develop training and skill set to support newly operationalized services
Assumptions GPaaS will be rolled out regardless of status of One Cloud; May have to manage complexities in tools if clouds are not converged
Issues & Risks Availability of One Cloud for eBay Inc. requested for implementation
Milestone | Completion | Status
GPaaS for Kraken | Q1 2014 | GREEN
ALTUS Environment Integration | Q1 2014 | GREEN
GPaaS for Java | Q2 2014 | GREEN
PP PDLC Self-Service Enablement | Q2 2014 | GREEN
GPaaS PP Stages on C3 | Q2 2014 | GREEN
Deployment Time Reduction | Q2 2014 | GREEN
Provisioning Time Reduction | Q2 2014 | GREEN
Altus - Next Gen | Q3 2014 | GREEN
Enable Local Development for PP | Q3 2014 | GREEN
Continuous Delivery | Q3 2014 | GREEN
PP Build Time Reduction | Q3 2014 | GREEN
GPaaS for C++ | Q4 2014 | GREEN
GPaaS - Container Based PaaS | Q4 2014 | GREEN
PaaS Auto-Remediation LOM | Q4 2014 | GREEN
Owner | Jigar Desai & Sergey Perov - GPF
Notes: Here are the elements of project charter with instructions

## Slide 3
Project: Developer Productivity – Cycle time

## Slide 4: Charter: Unification of Frameworks
Project Description GPF seeks to provide a single development experience by unifying the various development frameworks into one converged offering The unification of development frameworks across eBay Inc. will provide all developers the same architecture and tools across all environments.
Goal Unify development frameworks across MP and PP into a single offering that seeks to improve overall NPS amongst developers
Deliverables Offer a single Java platform across MP and PP Develop Commerce OS compliant service in MP Unify the Node.js applications for eBay Inc.; run Node.js apps on MP’s PaaS solution(GPaaS) Enable ebay Inc’s Python community to build/consume services and to deploy on GPaaS; Facilitate new app development based on the micro-services architecture achieving low-latency runtime Converge developer tools by integrating ICM with Altus and eSAMS for package and service lifecycle management
Dependencies GTO - Batch Scheduler Orchestration Operations GDI – Deliver MySQL, MongoDB as a database service on C3; Enable CaaS on Couchbase Streaming as a Service Converge PP & MP Hadoop instances Next Gen DAL GESE – Migrate all Stages to C3; Finalized architecture and roadmap for auto-remediation
Assumptions Adoption of unified development platform with existing customers and applications
Issues & Risks Lack of Product Management resources; Product Management resource ratio went from 1:8 to 1:18
Owner | Jigar Desai & Jai Sundararajan - GPF
Milestone | Completion | Status
Log Volume Reduction | Q2 2014 | GREEN
Initial Rollout of Applications with Unified Java Framework | Q2 2014 | GREEN
Spring Batch Rollout | Q2 2014 | GREEN
Unified Services Framework | Q2 2014 | GREEN
ALTUS Add-Ons | Q2 2014 | GREEN
Raptor Hooks for Next Gen DAL | Q2 2014 | GREEN
Python PDLC Operationalization; Enable Scala/squbs micro-services architecture for app development | Q3 2014 | GREEN
Unify Node.js stack , Run PayPal Node.js apps on GPaaS | Q2 2014 | GREEN
Notes: Here are the elements of project charter with instructions

## Slide 5
Project: Unification of Frameworks

## Slide 6: Charter: PPaaS / Commerce OS
Project Description The PPaaS / Commerce OS project seeks to provide a framework and automation support to incorporate business standards from each business organization. The PPaaS team and Commerce OS team each oversees the operating standards for PP and MP, respectively GPF seeks to simplify the integration of the standards and policies from these different and sometimes divergent teams. GPF will create frameworks, methodologies, and automations to improve the flow of standards to production for each team.
Goal Develop framework and automation support to incorporate business standards from each business organization
Deliverables Provide framework and automation support to enable business services across eBay Inc. Identify how to create services and manage their lifecycle Develop frameworks for integration of new standards and policies
Dependencies MP/PP Standards Teams - Definition of Standards across MP & PP
Assumptions The effort will not seek to integrate the two standards teams, only provide a more automated and consistent method to integrate the standards they develop The Commerce OS (MP) and PPaaS (PP) teams are driven by the two different business organizations (CTO)
Issues & Risks The existence and oversight of two teams may result in divergent directions for GPF
Milestone | Completion | Status
Implement Standards Body | Ongoing | GREEN
Identify Common Services | Ongoing | GREEN
Define Standards, Definitions, and Playbooks | Ongoing | GREEN
Implement Progressive Services | Ongoing | GREEN
Operationalize Services | Ongoing | GREEN
Owner | Jigar Desai & Jai Sundararajan - GPF
Notes: Here are the elements of project charter with instructions

## Slide 7
Project: PPaaS / Commerce OS

## Slide 8: Charter: Site Speed
Project Description The site speed project will increase the overall performance of the MP and PP sites while providing a means to monitor and measure the ongoing site speed for each business organization. GPF will work to provide enhanced site speed capabilities via the current CDN architecture. It will integration PP into the current efforts within MP. Efforts will be made to improve site speed as it relates to mobile devices and finally to secure the entire eBay Inc. site offerings.
Goal Provide enhanced site speed capabilities across MP and PP sites
Deliverables Incorporating PP into MP site speed efforts Utilize spdy protocol for mobile platforms Developing a single view dashboard for site speed Secure eBay using security certificate
Dependencies GPS - Extension of DSA requires Domain Un-sharding GFS - Completion of Akamai realignment project
Assumptions Application developers must incorporate the new site speed features in their applications – it will not happen automatically on the backend
Issues & Risks GPS must deliver on Domain Un-Sharding by the end of Q1 to move forward
Milestone | Completion | Status
Transition to spdy | Q3 2014 | GREEN
Deliver Site Speed Improvements | Q3 2014 | GREEN
Secure eBay | Q3 2014 | GREEN
Owner | Jigar Desai & Jai Sundararajan - GPF
Notes: Here are the elements of project charter with instructions

## Slide 9
Charter: Site Speed

## Slide 10: Charter: Services Operationalization
Project Description The services operationalization project will provide eBay Inc. with a resilient, virtualized services strategy that incorporates both MP and PP environments. GPF will work to develop a service configuration strategy encompassing resiliency of services. PP and Mica will be moved to a virtualized environment and ESB will be upgraded, merged, and deployed across all environments.
Goal Provide a resilient and virtualized services environment across MP and PP
Deliverables Establish resilient service configuration strategy and service virtualization strategy
Dependencies Customer Engineering - Partnership to design and architect Unifications as it pertains to node.js GPS - Integration into Product suite for tracking & reporting
Assumptions Must work across all GPI functions to ensure successful delivery of operationalized services
Issues & Risks
Milestone | Completion | Status
Configuration Strategy, Resiliency, and Virtualization for Services | Q2 2014 | GREEN
Upgrade, Merge, and Deploy ESB for PP | Q2 2014 | GREEN
Owner | Jigar Desai & Jai Sundararajan - GPF
Notes: Here are the elements of project charter with instructions

## Slide 11
Charter: Services Operationalization

## Slide 12: Charter: Next Gen Key Management
Project Description GPF seeks to provide a next generation key management product. Program is about deploying generic key management capability in PaaS which can be leveraged by any eBay Inc. property for managing keys and secrets securely.
Goal Single multi-tenant Key Management System as core GPaaS capability.
Deliverables Develop key management system comprising self-service portal for developers, key issuing service and Certificate Authority Implement easy to use encryption layer for Java, Node and C++ abstracting key management and encryption details from applications Migrate existing PayPal and Marketplace applications to new key management system and deprecate Protected Package
Dependencies GDI – Deliver MySQL as a database service on C3 Deliver MongoDB as a database service on C3 GCS – PCI compliant One Cloud for PayPal and Marketplace
Assumptions PCI Compliant GPI zone ready in time and accessible from both PayPal and Marketplace sides
Issues & Risks Tactical projects keep pulling key engineers from project. Adoption of framework patch to migrate existing apps on new KMS
Owner | Jigar Desai & Manish Pandey - GPF
Milestone | Completion | Status
Code Complete | Q2 2014 | GREEN
Deploy in QA | Q2 2014 | GREEN
Deploy in LIVE | Q3 2014 | GREEN
Notes: Here are the elements of project charter with instructions

## Slide 13: Charter: Security Intelligence (RL & RTD)
Project Description Prevention/reduction of Velocity attacks (DOS) on web flows and API calls in Market Places and PayPal.
Goal Integrate RL and RTD to reduce velocity attacks
Deliverables Migration to RL from TL on C++ stack in PayPal Piloting RL migration in Market Places Piloting RTD in Market Places Migration to RL from TL on JAVA stack in PayPal Migration of more flows/page to RL from TL in Market Places Begin RTD adoption in Market Places
Dependencies GDI - Decisions on EOL of Jetstream PD – Adoption support from vertical teams and regression support GFS – Capacity increase on RL servers Stage machine procurement for RL server
Assumptions RTD architecture and finalization of 3rd party components freezes in Q2
Issues & Risks Adoption and regression support is a risk Rate Liiter and RTD need to work with Akamai and Edge DOS/DDOS protection
Milestone | Completion | Status
Send money and request money flows on RL Login flow integration to RL in PayPal | Q1 2014 | GREEN
Completion of KT on RTD and RL in MP Migration to RL on C++ stack in PayPal Piloting RL migration in MP | Q2 2014 | GREEN
Piloting RTD in MP Migration to RL from TL on JAVA stack in PayPal | Q3 2014 | GREEN
Migrate more flows/pages to RL from TL in MP Begin RTD adoption in MP | Q4 2014 | GREEN
Owner | Jigar Desai & Srini Rangaraj- GPF
Notes: Here are the elements of project charter with instructions